## Sprint Number
ID | User Story | Tasks | Person Assigned | Status
3 | As a Production Company, I want to register an account, so that I can promote my movie that i have just released. | 3.1 Prepare the empty profile form. 3.2 Save data into the database as a profile 3.3 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
4 | As a Production Company, I want to register an account, so that I can see how big of a success my movie will be. | 4.1 Prepare the empty profile form. 4.2 Save data into the database as a profile 4.3 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
24 | As a logged in Movie producer, I want to submit a request to add a movie into the site, so that users can search up the movie. | 24.1 Prepare the empty Movie form. 24.2 Save data into the database as a New Movie. 24.3 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
25 | As a logged in site Admin, I want to accept the movie request made by the Movie producer, so that I can add more movie information to the site's database. | 25.1 Retrieve request data from the database for a New Movie. 25.2 Load movie data in the Movie form. 25.3 Accept movie date 25.4 Save data into the database as a Movie.2 25.5 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
26 | As a logged in site Admin, I want to decline the movie request made by the Movie producer, so that the site's movie information database will not include the movie that was requested. | 26.1 Retrieve request data from the database for a New Movie. 26.2 Load movie data in the Movie form. 26.3 Decline movie date. 26.4 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
27 | As a logged in site Admin, I want to add the movie information I have accepted from the Movie producer, so that users can find and view this movie. | 27.1 Retrieve request data from the database for the accepted New Movie. 27.2 Save data to database for accepted movies. 27.3 Load movie data in the Movie form. 27.4 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
29 | As a logged in site Admin, I want to remove the movie information based on reports by Movie producers of the site, so that movies will not appear in user's search results. | 29.1 Retrieve request data from the database for the removed Movie. 29.2 Delete data from the database of accepted movies for the removed movie. 29.3 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
32 | As a logged in Movie producer, I want to send information about the newly accepted movie to the site Admin, so that the Admin can add a new movie with correct information onto the site. | 32.1 Send producer's info about new movie to database. 32.2 Retrieve producer's info about new movie from the database. 32.3 Send this data to the database for admin. 32.4 Updates data for producer's info for new movie. 32.5 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
7 | As a Movie Critic, I want to register an account, so I can submit reviews for movies I have seen. | 7.1 Prepare the empty profile form. 7.2 Save data into the database as a profile. 7.3 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
8 | As a Movie Critic, I want to register an account, so I can build my platform of followers. | 8.1 Prepare the empty profile form. 8.2 Save data into the database as a profile. 8.3 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
12 | As a registered critic, I want to login into the web, so that I can use the web to know more information about different movies. | 12.1 Prepare the empty profile form. 12.2 Save data into the database as a profile. 12.3 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
16 | As a logged in user, I want to write a review so that others can form opinions on the movie. | 16.1 Send review data to database. 16.2 Admin accepts or rejects review. 16.3 Save review data to databse for accepted reviews. 16.4 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
17 | As a logged in user, I want to leave a constructive review so that producers can recieve feedback about their movies. | 17.1 Send review data to database. 17.2 Admin accepts or rejects review. 17.3 Save review data to databse for accepted reviews. 17.4 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
18 | As a guest user, I want to search reviews so that i can get the best recommendations | 18.1 Select search data to database. 18.2 Received relevant reviews from database. 18.3 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
19 | As a critic, I want to edit a review so that I can update my opinion. | 19.1 Send review to database. 19.2 Admin accepts or declines edits. 19.3 Load review to page. 19.4 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
21 | As a producer, I want to leave a review so that I can share my tips with other producers. | 21.1 Send review data to database. 21.2 Admin accepts or declines edits. 21.3 Load review to page. 21.4 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
22 | As a critic, I want to delete a review so that I can withdraw my viewpoint. | 22.1 Send deleted review data to database. 22.2 Admin accepts or declines edits. 22.3 Load new ratings page. 22.4 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
23 | As a critic, I want to leave a rating so that viewers will quickly understand my opinion. | 23.1 Send deleted review data to database. 23.2 Admin accepts or declines edits. 23.3 Load new ratings page. 23.4 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
28 | As a logged in site Admin, I want to edit the movie information based on reports by users of the site, so that the movie information is corrected. | 28.1 Send edited movie data to database. 28.2 Admin accepts or declines edits. 28.3 Load new movie info page. 28.4 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
30 | As a logged in site member, I want to report a movie's description for spelling/grammar mistakes, so that the admin will be notified to fix this mistake. | 30.1 Send reported movie data to database. 30.2 Admin accepts or declines edits. 30.3 Load new ratings page. 30.4 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
31 | As a logged in Movie producer, I want to report to remove a movie that exists on the site, so that incorrect movies will not appear in the user's search results. | 31.1 Send reported movie data to database. 31.2 Admin accepts or declines edits. 31.3 Load new ratings page. 31.4 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
33 | As a logged in Admin, I want to accept the review request a critic user has submitted, so that users of the site can see the review of this movie. | 33.1 Retrieve request data from the database for a review request. 33.2 Load Review request. 33.3 Accept Critic review 33.4 Save data into the database as a Review 33.5 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
34 | As a logged in Admin, I want to deny a movie review request send by the critic, so that this request will not be included into the movie's reviews. | 34.1 Send reported movie data to database. 34.2 Admin accepts or declines edits. 34.3 Load new ratings page. 34.4 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
35 | As a logged in site Admin, I want to review and decline critic requests that have been submitted, so that the critic won't be able to sent reviews. | 35.1 Retrieve request data from the database for a review request. 35.2 Load Critic request. 35.3 Decline Critic request. 35.4 Delete Critic Request data from user database. 35.5 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed
36 | As a logged in site Admin, I want to review and accept critic requests that have been submitted, so that the site will have Critic users to create reviews. | 36.1 Send reported movie data to database. 36.2 Admin accepts or declines edits. 36.3 Load new ratings page. 36.4 Commit, push and merge the functionalities. | Carlin McNamara (s3784664) | Completed