## Sheet1
COSC1076 ¦ Semester 1 2021
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name:
Group Member: | A | James | Progress Classes: | Ahead
Group Member: | B | Bill |  | On-track
Group Member: | C | Varun |  | Behind
Group Member: | D | Muhammad |  | Way Behind
Tutor: | Nan Gao
Class: | Monday 8:30am 14.10.31
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | A | B | C | D
|  |  | Group Formed |  | Weekly Contribution | Done Git Repo | Done MS Teams | Done Tasks Planning
|  |  | MS Team created |  | Issues
|  |  | Git Repo created |  | Other Notes
|  | Progress | On-track
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | A | B | C | D
|  |  | Choice of where to use linked list, vector & array |  | Weekly Contribution | Worked on user prompts and LinkedLists implementation. | Going of the ADTs in the spec, helped create the LinkedList implementation, wrote a basic main menu skeleton code, amd started looking at gameplay logic. | Done Main Menu main logic
|  |  | Initial Design of ADTs (classes and potential methods) |  | Issues | restriciting user prompts to valid inputs only. | Save/load functionality starte instead of gameplay logic | figuring out methods needed and flow of program.
|  |  | Main menu |  | Other Notes
User Prompt (for gameplay), but no/minimal error checking
Linked List implementation
Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required
ADT implementation for storing information, game loop logic not required
|  | Progress | On-track
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | A | B | C | D
|  |  | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) |  | Weekly Contribution | Worked on gameplay for a single round. | Worked on save/load functions more, basic file format/input validation started | Helping with single round and save/load functions.
|  |  | Initialisation of data strctures for new game |  | Issues | Transfering tiles from player's hand to gameboard. | save/load functionality taking longer than expected | Writing code with less repetition and better coding styles.
|  |  | Write Tests Cases for common uses |  | Other Notes |  | Starting to drag behind in workload, other courses work beginning to become a factor
Gameplay for single round, that is selecting and moving of tiles from a factory to players mosaic
|  | Progress | On-track
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | A | B | C | C
|  |  | Fully complete implementation and error free |  | Weekly Contribution | Tests, scoring, bug fixing. | EOF operations, testing according to tests, bug fixing | Helped with tests. scoring and bugs.
|  |  | Full error checking of user prompt |  | Issues | Endgame scoring giving errors. | unsure of legality of exit() function/keyword, included anyway | Restricting tile placement. Finding all possible user paths.
|  |  | Automated placement of tiles at end of round, but no scoring |  | Other Notes |  | Last week rush to complete meant bug fixing not complete | Working with less people was a challenge, but glad we could get through it.
Final Tests
Group Report Written
|  | Progress | On-track